Readability of Online Patient Education Materials for Pre-Procedure Cardiac CT, With an AI Rewrite Arm

Project Plan

Author: Naeem

# 1. What We Are Doing

We are measuring how hard online patient education pages are to read for three cardiac CT procedures: pre-TAVR planning, coronary CTA, and left atrial appendage closure (Watchman/LAAO). These are pages patients read before they consent to a procedure, so reading level matters a lot.

Past work has looked at cardiac MRI pages and at interventional radiology pages, but not at these pre-procedure cardiac CT pages. That gap is the novel part.

We add a second arm: we take each page, ask three AI chatbots to rewrite it at a 6th-grade level, and then check two things. First, did the reading level actually drop. Second, did the rewrite stay medically correct and complete. The reading-level-versus-accuracy trade-off is the part nobody has measured well, so it is what makes the paper hard to scoop.

## Aims

- Aim 1: Measure the reading level of existing pre-procedure cardiac CT pages across several major websites.

- Aim 2: Measure whether AI rewrites lower the reading level.

- Aim 3: Measure whether the AI rewrites stay accurate and complete, scored by a subspecialist.

# 2. Background Reading (Do This First)

Read these before touching any data. They tell us the standard methods and what has already been done.

- McEnteggart, Naeem et al., J Vasc Interv Radiol 2015 (PMID 25935147) — the readability method we are building on.

- Piersson et al., 2025 — readability of cardiac MRI patient pages. This is the closest recent paper. Read it to see what we should NOT repeat.

- Behers et al., Cureus 2024 — readability of AI chatbot answers about cardiac catheterization. Read it for the AI scoring approach.

- The PEMAT tool (Patient Education Materials Assessment Tool) from AHRQ — we may use this for understandability and actionability.

Goal of this step: write one page in your own words on what is already known and what our gap is. This becomes the intro of the paper.

# 3. Picking the Pages to Study (The Sample)

We need a fixed, reproducible way to pick pages so a reviewer cannot say we cherry-picked.

Procedures (3):

- Pre-TAVR cardiac CT

- Coronary CTA

- Left atrial appendage closure CT (Watchman / LAAO)

Websites to search:

Use the major patient-facing sites. Suggested list: RadiologyInfo.org, the American Heart Association, the American College of Cardiology (CardioSmart), the British Heart Foundation, Mayo Clinic, Cleveland Clinic, and the top hospital pages that show up in search. Lock this list before you start.

How to find pages (write the exact steps down):

- Use one browser in private/incognito mode, signed out, with location set the same way each time.

- Search each procedure name in Google. Record the date range of the search (for example, a single week).

- Take the patient-education pages from the chosen sites that appear in, say, the first 2 pages of results.

- Save each page as text. Strip out menus, headers, footers, ads, captions, and reference lists. Keep only the body text patients would read.

Inclusion and exclusion:

- Include: English-language pages written for patients about the procedure.

- Exclude: pages aimed at doctors, video-only pages, pages behind a login, and duplicates.

Aim for roughly 20 to 40 pages total. Keep a simple spreadsheet: site name, procedure, URL, date captured, word count.

# 4. Measuring Reading Level (Aim 1)

Run each cleaned page through the standard readability formulas. Use the same six the field uses so we can compare to past papers:

- Flesch-Kincaid Reading Ease (FKRE)

- Flesch-Kincaid Grade Level (FKGL)

- Gunning-Fog Index (GFI)

- Simple Measure of Gobbledygook (SMOG)

- Coleman-Liau Index (CLI)

- Automated Readability Index (ARI)

How to compute them:

Write a short Python script using the textstat library. Feed it the cleaned text file for each page and have it output a row per page with all six scores plus word count, sentence count, average words per sentence, and average syllables per word. Save to CSV. Do not score by hand.

Sanity check: hand-verify the scores on 2 or 3 pages with an online calculator to confirm the script is correct.

The benchmark:

The NIH and American Medical Association recommend patient materials be written at about a 6th-grade level. Report how many pages meet that and how many do not.

# 5. The AI Rewrite Arm (Aim 2)

For each original page, generate a rewritten version from three different chatbots (for example, ChatGPT, Claude, and Gemini). Use the exact same prompt every time.

Standard prompt (use word for word, log the date and model version):

Rewrite the following patient education text at a 6th-grade reading level. Keep all medical facts accurate. Do not add new medical claims. Do not remove important safety or preparation information. Use plain words and short sentences.

Then run all rewritten versions through the same six-formula script from Section 4. Now you have before-and-after scores.

What to record per page and per model:

- All six readability scores, before and after.

- Word count before and after (did it get shorter or longer).

- The model name and version, and the date generated.

# 6. Checking Accuracy of the Rewrites (Aim 3 — the novel core)

A rewrite is useless if it drops the reading level but loses or distorts the medicine. So a subspecialist (Naeem, or a blinded second reader) scores each rewritten page on a simple rubric.

Scoring rubric (1 to 5 each):

- Accuracy: are all medical statements correct?

- Completeness: did it keep the key prep, risk, and safety points from the original?

- Added errors: did it invent anything not in the original? (reverse-scored)

To reduce bias: strip the model name off each rewrite, shuffle the order, and have the reader score them blind. If you can get a second reader for even a subset, report agreement between the two.

# 7. Statistics Plan

Keep it simple and standard. A biostatistician should confirm, but here is the plan:

- Describe the original pages: mean and SD for each of the six scores, overall and by website and by procedure.

- Aim 1 comparison across websites: ANOVA (or Kruskal-Wallis if data are skewed) for each score.

- Aim 2 before-vs-after: paired test (paired t-test or Wilcoxon signed-rank) for each score, original vs each model's rewrite.

- Compare the three models to each other: repeated-measures ANOVA or Friedman test.

- Aim 3: report mean rubric scores per model; correlate reading-level drop against accuracy/completeness to show the trade-off.

Set significance at p < 0.05. Decide and write the full stats plan BEFORE running anything, so it is not fishing.

# 8. Who Does What

| Task | Owner |
| --- | --- |
| Background reading + intro draft | Abdul |
| Sample selection + page capture + cleaning | Abdul |
| Python readability script (textstat) + CSV | Abdul (AI PhD — good fit) |
| Running the 3 chatbots with the fixed prompt | Abdul |
| Accuracy/completeness scoring (subspecialist) | Naeem (blinded second reader if possible) |
| Statistics | Abdul + biostatistician check |
| Clinical framing, novelty, final edits | Naeem |

# 9. Rough Timeline

| Weeks | Milestone |
| --- | --- |
| 1-2 | Background reading, lock the site list and the prompt, write the stats plan |
| 3-4 | Capture and clean all pages, build the spreadsheet |
| 5 | Run readability script on originals (Aim 1 done) |
| 6-7 | Generate AI rewrites, re-run script (Aim 2 done) |
| 8-9 | Blinded accuracy scoring (Aim 3 done) |
| 10-11 | Statistics and figures |
| 12-14 | Write the manuscript |

# 10. Final Deliverables

- One clean spreadsheet of all pages and all scores (before and after).

- The Python script, saved and documented so anyone can rerun it.

- The blinded accuracy scores.

- A manuscript draft targeting a cardiac imaging or radiology journal.

# 11. Things That Can Go Wrong (Watch For These)

- Web pages change. Save the text the day you capture it and record the date.

- Messy text inflates scores. Stray menu text, captions, and references skew the formulas, so clean carefully and clean the same way every time.

- Model versions change. Write down the exact model and date for every rewrite, because results may not reproduce later.

- Accuracy scoring bias. Always score blind to which model wrote it.

- Too few pages. If a procedure has very few good pages, report that honestly rather than padding the sample.